## ECN
Engineering Change Notice
ORIGINAL PART/PROCESS/DRAWING NO. |  | ECN NO. | PROBLEM DESCRIPTION
GF0777B-1X |  | CE-ECN-010623-GF0777B-1X | Frame tooling has gone EOL
UPDATED PART/PROCESS/DRAWING NO. |  | ECN REV NO. | PART/PROCESS/DRAWING CHANGE
GF0777B-1X |  | A | New tooling for the speaker frame
REASON FOR CHANGE
The tooling for this speaker frame has gone EOL and has been replaced with an equivalent. Apart from a slightly wider tolerance for the mounting holes, there will be no physical changes to the part and the new parts will match the current parts in form, fit, and functionality. See attached figure 1 for a visual comparison and figure 2 for an acoustic performance comparison.
DESCRIPTION OF CHANGE
Replace EOLed Speaker Frame Tooling
AFFECTED DOCUMENTS/PARTS/PROCESSES
GF0777B-1X Spec GF0777B-1X Frame Tooling
ORIGINATOR NAME |  |  | ORIGINATOR SIGNATURE |  |  | DATE
Jason Li | [5 empty] | 2023-01-06
APPROVAL
REQUIREMENTS
IS THE ECN ENTIRELY FILLED OUT?
IS THE ORIGINAL DRAWING ATTACHED?
IS THE UPDATED DRAWING ATTACHED?
| ARE ALL AFFECTED PARTIES INFORMED? |  |  |  |  | DUE DATE
| IS THE DUE DATE UNDERSTOOD? |  |  |  |  | 2023-01-06
EXECUTION
| MODIFY EXISTING PART/PROCESS/DRAWING |  |  | SCRAP EXISTING MANUFACTURED PARTS
| CREATE NEW PART/PROCESS/DRAWING |  |  | KEEP EXISTING MANUFACTURED PARTS
TEAM MEMBER NAME |  |  | TEAM MEMBER SIGNATURE |  |  | DATE
Peter Tai |  |  | PT |  |  | 2023-01-06
TEAM MEMBER NAME |  |  | TEAM MEMBER SIGNATURE |  |  | DATE
Josh Klyman |  |  | JK |  |  | 2023-01-06
TEAM MEMBER NAME |  |  | TEAM MEMBER SIGNATURE |  |  | DATE
Craig Schroeder |  |  | CS |  |  | 2023-01-06
TEAM MEMBER NAME |  |  | TEAM MEMBER SIGNATURE |  |  | DATE
Jason Li |  |  | JL |  |  | 2023-01-06
APPROVER NAME |  |  | APPROVER SIGNATURE |  |  | DATE
Joshua Klyman | [5 empty] | 2023-01-09
| CHALLENGE ELECTRONICS |  | PHONE: 1(800)722-8197 |  | DOC NO. CE-ECN-061317
| 95 EAST JEFRYN BOULEVARD |  | EMAIL: SALES@CHALLELEC.COM
| DEER PARK, NY 11729 |  | WEB: CHALLENGEELECTRONICS.COM
YES
YES
YES
YES
YES
NO
NO
NO
NO
NO

## Figures
Current | New
Figure 1. Visual Comparison
Figure 2. Response Curve Comparison