## ECN
Engineering Change Notice
ORIGINAL PART/PROCESS/DRAWING NO. |  | ECN NO. | PROBLEM DESCRIPTION
CT12P-20S400-7 CSPT12A03-4.0F CSPT12A03-4.0F-1 CSPT12A09-4.0F CSPT12B03-4.0F CSPT12D05-4.0F CEPT120L030-120-24MHR CEPT120R030-120-2700MHR |  | CE-ECN-060721-CT12 | The current printing process can be readily replaced with a more efficient method.
UPDATED PART/PROCESS/DRAWING NO. |  | ECN REV NO. | PART/PROCESS/DRAWING CHANGE
CT12P-20S400-7 CSPT12A03-4.0F CSPT12A03-4.0F-1 CSPT12A09-4.0F CSPT12B03-4.0F CSPT12D05-4.0F CEPT120L030-120-24MHR CEPT120R030-120-2700MHR |  | A | Change the current printing method from ink printing process to a laser printing process.
REASON FOR CHANGE
The factory has in place a laser printer that is used for the production of other parts. This printer is more efficient and environmentally friendly than the current color printer and so to improve output, the factory will use this printer for all future production of the listed transducers. The new markings will have a different appearance but there will have no change in performance between processes. See figure 1.
DESCRIPTION OF CHANGE
Change the equipment of printing from single color pad printing machine to laser marking machine. See production change in Figure 2.
AFFECTED DOCUMENTS/PARTS/PROCESSES
Work Instructions for the following: CT12P-20S400-7 CSPT12A03-4.0F CSPT12A03-4.0F-1 CSPT12A09-4.0F CSPT12B03-4.0F CSPT12D05-4.0F CEPT120L030-120-24MHR CEPT120R030-120-2700MHR
ORIGINATOR NAME |  |  | ORIGINATOR SIGNATURE |  |  | DATE
Jason Li | [5 empty] | 2021-06-07
APPROVAL
REQUIREMENTS
IS THE ECN ENTIRELY FILLED OUT?
IS THE ORIGINAL DRAWING ATTACHED?
IS THE UPDATED DRAWING ATTACHED?
| ARE ALL AFFECTED PARTIES INFORMED? |  |  |  |  | DUE DATE
| IS THE DUE DATE UNDERSTOOD? |  |  |  |  | 2021-06-07
EXECUTION
| MODIFY EXISTING PART/PROCESS/DRAWING |  |  | SCRAP EXISTING MANUFACTURED PARTS
| CREATE NEW PART/PROCESS/DRAWING |  |  | KEEP EXISTING MANUFACTURED PARTS
TEAM MEMBER NAME |  |  | TEAM MEMBER SIGNATURE |  |  | DATE
James Zhu |  |  | JZ |  |  | 2021-06-07
TEAM MEMBER NAME |  |  | TEAM MEMBER SIGNATURE |  |  | DATE
William Wang |  |  | WW |  |  | 2021-06-07
TEAM MEMBER NAME |  |  | TEAM MEMBER SIGNATURE |  |  | DATE
David Zhang |  |  | DZ |  |  | 2021-06-07
TEAM MEMBER NAME |  |  | TEAM MEMBER SIGNATURE |  |  | DATE
Josh Klyman |  |  | JK |  |  | 2021-06-07
TEAM MEMBER NAME |  |  | TEAM MEMBER SIGNATURE |  |  | DATE
Craig Schroeder |  |  | CS |  |  | 2021-06-07
TEAM MEMBER NAME |  |  | TEAM MEMBER SIGNATURE |  |  | DATE
Jason Li |  |  | JL |  |  | 2021-06-07
APPROVER NAME |  |  | APPROVER SIGNATURE |  |  | DATE
Jason Li | [5 empty] | 2021-06-07
| CHALLENGE ELECTRONICS |  | PHONE: 1(800)722-8197 |  | DOC NO. CE-ECN-061317
| 95 EAST JEFRYN BOULEVARD |  | EMAIL: SALES@CHALLELEC.COM
| DEER PARK, NY 11729 |  | WEB: CHALLENGEELECTRONICS.COM
YES
YES
YES
YES
YES
NO
NO
NO
NO
NO

## Figures
Figure 1. Marking Change Example
Figure 2. Machine Change
Change To
Change To