## ECN
Engineering Change Notice
ORIGINAL PART/PROCESS/DRAWING NO. |  | ECN NO. | PROBLEM DESCRIPTION
TDB05LFPN |  | CE-ECN-080621-TDB05LFPN | The current printing process can be readily replaced with a more efficient method.
UPDATED PART/PROCESS/DRAWING NO. |  | ECN REV NO. | PART/PROCESS/DRAWING CHANGE
TDB05LFPN |  | A | Change the current printing method from a screen printing process to a laser printing process.
REASON FOR CHANGE
The factory has in place a laser printer that is more efficient and environmentally friendly than the current screen printer and so to improve output, the factory will use this printer for all future production of the TDB05LFPN. The new markings will have a different appearance but there will have no change in performance between processes. See figure 1.
DESCRIPTION OF CHANGE
Change the printing equipment from a screen printing machine to a laser printing machine.
AFFECTED DOCUMENTS/PARTS/PROCESSES
TDB05LFPN Work Instruction
ORIGINATOR NAME |  |  | ORIGINATOR SIGNATURE |  |  | DATE
Jason Li | [5 empty] | 2021-08-06
APPROVAL
REQUIREMENTS
IS THE ECN ENTIRELY FILLED OUT?
IS THE ORIGINAL DRAWING ATTACHED?
IS THE UPDATED DRAWING ATTACHED?
| ARE ALL AFFECTED PARTIES INFORMED? |  |  |  |  | DUE DATE
| IS THE DUE DATE UNDERSTOOD? |  |  |  |  | 2021-08-06
EXECUTION
| MODIFY EXISTING PART/PROCESS/DRAWING |  |  | SCRAP EXISTING MANUFACTURED PARTS
| CREATE NEW PART/PROCESS/DRAWING |  |  | KEEP EXISTING MANUFACTURED PARTS
TEAM MEMBER NAME |  |  | TEAM MEMBER SIGNATURE |  |  | DATE
Jane Yang |  |  | JY |  |  | 2021-08-06
TEAM MEMBER NAME |  |  | TEAM MEMBER SIGNATURE |  |  | DATE
Josh Klyman |  |  | JK |  |  | 2021-08-06
TEAM MEMBER NAME |  |  | TEAM MEMBER SIGNATURE |  |  | DATE
Craig Schroeder |  |  | CS |  |  | 2021-08-06
TEAM MEMBER NAME |  |  | TEAM MEMBER SIGNATURE |  |  | DATE
Jason Li |  |  | JL |  |  | 2021-08-06
APPROVER NAME |  |  | APPROVER SIGNATURE |  |  | DATE
Jason Li | [5 empty] | 2021-08-06
| CHALLENGE ELECTRONICS |  | PHONE: 1(800)722-8197 |  | DOC NO. CE-ECN-061317
| 95 EAST JEFRYN BOULEVARD |  | EMAIL: SALES@CHALLELEC.COM
| DEER PARK, NY 11729 |  | WEB: CHALLENGEELECTRONICS.COM
YES
YES
YES
YES
YES
NO
NO
NO
NO
NO

## Figures
Figure 1. Marking Change
Change To